STATEMENT OF WORK

BA4E – AI Powered Consulting Diagnostics & Advisory Platform

MVP – Phase 1  |  WhatsApp Diagnostics · AI Advisory · PDF Scorecards · Consultant Portal

Prepared For:  Business Advice for Expansion (BA4E)

Prepared By:  CXION Technologies

Document Version:  v1.0

Date:  May 2026

Classification:  Confidential

This document is prepared exclusively for Business Advice for Expansion (BA4E). Unauthorised distribution is strictly prohibited.

# 1.  Document History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| v1.0 | May 2026 | CXION Technologies | Initial SOW — BA4E AI Consulting & Advisory Platform MVP Phase 1 |
| — | — | Pending client review | To be updated post-sign-off |

# 2.  Table of Contents

All sections are listed below. Open in Microsoft Word and press Ctrl+A → F9 to populate page numbers automatically.

| Section | Title |
| --- | --- |
| 3 | Executive Summary |
| 4 | Business Objectives |
| 5 | Expected Business Outcomes |
| 6 | Project Scope — MVP Phase 1 |
| 7 | Out of Scope — Future Phases |
| 8 | Technology Stack |
| 9 | Security & Compliance |
| 10 | Deliverables Summary |
| 11 | Team Structure |
| 12 | Project Timeline & Milestones |
| 13 | Testing & Acceptance |
| 14 | Deployment & Go-Live |
| 15 | Assumptions |
| 16 | Risks & Dependencies |
| 17 | Change Request Process |
| 18 | Support & Maintenance |
| 19 | Commercials |
| 20 | Agreement & Sign-Off |

# 3.  Executive Summary

Business Advice for Expansion (BA4E) is a specialist supply chain consulting practice delivering diagnostics, advisory, and capability-building services to SMB and enterprise clients across manufacturing, pharma, FMCG, and logistics sectors. Current consulting engagement is delivered manually — through in-person sessions, spreadsheets, and unstructured communications — creating constraints in lead qualification consistency, diagnostic scalability, and time-to-value.

BA4E has engaged CXION Technologies  to design, build, and deploy an AI-powered, cloud-hosted automation platform that digitises its consulting diagnostics and advisory workflows. The MVP — Phase 1 — focuses on the core value-delivery layer: a WhatsApp-native conversational diagnostic engine, a future AI-assisted consultant advisory capability, a dynamic PDF scorecard engine, and a role-based consultant management portal.

## Phase 1 Objectives

- Capture and qualify leads through automated WhatsApp diagnostic conversations

- Deliver instant AI-generated supply chain scorecards with benchmarks and recommendations

- Provide AI-assisted advisory recommendations for BA4E consultants using BA4E's proprietary knowledge base.

- Centralise consultant operations in a secure, role-based web portal

- Establish a cloud-native, modular technical foundation for Phase 2 and Phase 3 expansion

The MVP is scoped for delivery in 8 weeks at a total fixed price of 21000 USD. The architecture is container-based and designed for seamless addition of Phase 2 (expanded diagnostics, capability-building, AI coaching) and Phase 3 (enterprise web portal, LMS, ERP integrations) without rearchitecting the core platform.

# 4.  Business Objectives

The following objectives govern this engagement and are aligned to BA4E's consulting digitisation and growth strategy:

| # | Objective | Expected Business Impact |
| --- | --- | --- |
| 1 | Digitise consulting diagnostic workflows | Eliminate manual data collection; standardise every diagnostic interaction |
| 2 | Reduce manual consulting effort | Automate repetitive intake and scoring; free consultants for high-value advisory |
| 3 | Improve lead generation and customer onboarding | Diagnostic responses centrally captured for consultant review and follow-up. |
| 4 | Deliver AI-powered recommendations at scale | Enable BA4E consultants to securely access AI-assisted advisory recommendations through the Consultant Portal. |
| 5 | Improve customer engagement and experience | Instant scorecards and AI responses reduce time-to-value for every client |
| 6 | Centralise consultant operations | Single portal for leads, diagnostics, reports, and customer management |
| 7 | Standardise consulting processes | Uniform diagnostic flows ensure consistent quality across all engagements |
| 8 | Create a scalable, modular architecture | Phase 2 and Phase 3 features added without platform rebuild |

# 5.  Expected Business Outcomes

Successful delivery of the MVP Phase 1 platform is expected to generate the following measurable outcomes:

| Outcome | Measurement Indicator |
| --- | --- |
| Faster customer onboarding | Diagnostic completion reduced from days to under 10 minutes |
| Improved lead conversion rate | All diagnostic responses centrally stored and accessible within the Consultant Portal. |
| Reduced manual consulting effort | All repetitive diagnostic intake and scoring fully automated |
| Centralised customer information | All diagnostic history, scorecards, and notes in one consultant portal |
| Consultant advisory support foundation | Platform prepared for future AI-assisted consultant advisory workflows |
| Instant PDF scorecard generation | Dynamic scorecard delivered within 60 seconds of diagnostic completion |
| Foundation for future AI expansion | Architecture supports Phase 2 (expanded diagnostics, LMS) without rework |

# 6.  Project Scope — MVP Phase 1

The MVP Phase 1 scope comprises seven integrated components. The engagement is structured as four 2-week sprints, each delivering a defined increment of the platform.

## A.  WhatsApp Diagnostic Platform

| Item | Details |
| --- | --- |
| Objective | Convert WhatsApp traffic into qualified supply chain leads in under 10 minutes through automated conversational diagnostics |
| Entry Channels | WhatsApp QR code • Website 'Start Diagnostic' button • Embedded widget • Direct WhatsApp link |
| Onboarding | Name • Email • Phone • Company Name • Industry • Business Type • Consent capture • Lead source tracking |
| Diagnostic Categories | Category A: Supply Chain Operations Diagnostic (Context & Firmographics • Pain Points • Quantitative Metrics • Instant Value Assessment) Category B: Digital Supply Chain Maturity Audit (Technology Stack • Workflow Automation • Value Leakage) |
| Conversational UX | Interactive buttons • List menus • Minimal typing • Mixed-initiative conversation flow • Context-aware session management |
| Outputs | Maturity score (0–9) • Industry benchmark • Top 3 recommendations • PDF scorecard delivery within 60 seconds • Diagnostic stored within the Consultant Management Platform for follow-up and advisory workflows. |

## B.  Website Embedded Chatbot

| Item | Details |
| --- | --- |
| Objective | Enable customer engagement and lead capture through BA4E's website in addition to the WhatsApp channel |
| In Scope | JavaScript embed widget • Shared diagnostic backend • Lead capture • PDF scorecard via email from website channel |

## C.  Diagnostic Scoring Engine

| Item | Details |
| --- | --- |
| Objective | Implement BA4E's deterministic scoring matrices with real-time maturity classification and benchmark comparison |
| Scoring Model | 1–3 score per pillar • 3–9 total score • Digital Drag Coefficient calculation |
| Industry Rules | Separate scoring weight matrices per sector: Manufacturing, Pharma, FMCG, Logistics |
| Maturity Levels | 0–3 → Critical (Survival Mode) ¦ 4–6 → Emerging (Unstable Growth) ¦ 7–8 → Structured (Controlled Operations) ¦ 9 → Advanced (Scalable & Optimized) |

## D.  Dynamic PDF Scorecard Engine

| Item | Details |
| --- | --- |
| Objective | Auto-generate a branded BA4E Diagnostic Scorecard on diagnostic completion and deliver it via WhatsApp within 60 seconds |
| Scorecard Contents | Customer details • Overall score and maturity badge • Pillar-by-pillar RAG breakdown • Industry benchmark matrix • Top 3 findings • Top 3 recommendations • Consulting call-to-action |
| Technology | ReportLab or WeasyPrint — BA4E-branded templates; auto-generated on diagnostic completion |
| Deliverable | PDF delivered via WhatsApp (or email from website channel) within 60 seconds of completion |

### D.1  Sample Scorecard Layout

The final scorecard layout, branding guidelines, visual design elements, KPI presentation format, and advisory presentation structure will be provided and approved by BA4E during the detailed design and UX review phase.

## E.  Consultant Advisory Assistance (Future Phase Enhancement)

| Item | Details |
| --- | --- |
| Objective | Establish the foundational workflow and platform extensibility required to support future AI-assisted consultant advisory capabilities within the Consultant Portal. |
| MVP Scope | Consultant-facing workflow preparation, advisory note management, customer context visibility, and extensible architecture support for future AI integration. |
| Future Enhancement | Advanced AI advisory capabilities including Retrieval-Augmented Generation (RAG), semantic knowledge retrieval, contextual AI recommendations, and vector database integration are planned for a future phase beyond MVP Phase 1. |
| Future Technology Direction | LangChain + OpenAI GPT-4o + ChromaDB (Vector Database) |
| Proposed Future Knowledge Sources | BA4E diagnostic frameworks • SOPs • Industry benchmarks • Internal best-practice guides • Approved case studies (anonymised) |
| Proposed Capabilities | Knowledge retrieval assistance for consultants • Context-aware recommendation support • Diagnostic-based insight suggestions • Internal consultant advisory workflows • Knowledge search and summarization |
| Access Model | Any future AI-assisted advisory capability will be accessible only to authorized BA4E consultants within the secure Consultant Portal and will not be directly exposed to end customers. |
| Business Outcome | Enable consultants to improve advisory consistency, reduce manual research effort, and accelerate customer engagement workflows through AI-assisted knowledge support. |

## F.  Role-Based Consultant Portal

| Item | Details |
| --- | --- |
| Objective | Centralise all BA4E consultant operations — leads, customers, diagnostics, reports, future AI advisory workflow support — in one secure web portal |
| Modules | Dashboard (KPIs, activity feed, quick actions) • Lead Management • Customer Management • Diagnostic Reports (view, download, share) • AI Advisory Log (interactions, escalations) • Administration (users, roles, APIs) |
| Roles | Administrator (full access) • Consultant (operational access) • Reviewer (read-only) |
| Technology | Next.js + TypeScript + Tailwind CSS • JWT authentication • RBAC on all endpoints |
| Business Outcome | Centralised consultant operations; full visibility of all leads, diagnostics, and future AI advisory workflow support in one place |

# 7.  Out of Scope — Future Phases

The following items are explicitly excluded from the MVP Phase 1 engagement. These capabilities are planned for Phase 2 and Phase 3 and will be delivered under separate Statements of Work. Any request to include these items within Phase 1 requires a formal signed Change Order.

| Excluded Item | Planned Phase |
| --- | --- |
| Automated capability-building workflows and micro-learning engine | Phase 2 |
| Personalised learning paths and role-based training delivery | Phase 2 |
| AI coaching workflow and AI-guided learning | Phase 2 |
| Quizzes, assessments, and skill evaluations | Phase 2 |
| Certification and skill badge engine | Phase 2 |
| Learning Management System (LMS) functionality | Phase 2 |
| Diagnostic Categories C–G (Cost, Operational, Strategy, Manufacturing, Pharma) | Phase 2 |
| Advanced analytics and capability heatmaps | Phase 2 / Phase 3 |
| ERP, WMS, and TMS system integrations | Phase 3 |
| Enterprise web client portal with full benchmarking and diagnostic history | Phase 3 |
| Multi-tenant architecture and organisational governance | Phase 3 |
| Multi-language support beyond English | Phase 2 |
| LeadConnector CRM integration and automated CRM workflows | Phase 2 |

# 8.  Technology Stack

The platform is built on a cloud-native, containerised technology stack selected for reliability, AI capability, and long-term modularity.

| Layer | Technology | Purpose | Phase |
| --- | --- | --- | --- |
| Frontend | Next.js + TypeScript + Tailwind | Consultant portal, website chatbot widget | Phase 1 |
| Backend | FastAPI (Python 3.11+) | API layer, business logic, scoring engine, webhook processing | Phase 1 |
| Database | PostgreSQL (AWS RDS) | Structured data — profiles, diagnostics, scores, sessions | Phase 1 |
| AI Orchestration | LangChain + OpenAI GPT-4o | Future consultant advisory assistance | Phase 1 |
| Vector Database | ChromaDB | Future semantic retrieval for consultant advisory workflows | Phase 1 |
| PDF Engine | ReportLab / WeasyPrint | Dynamic PDF scorecard generation | Phase 1 |
| Messaging | WhatsApp Business API (Meta) | Conversational flows, interactive buttons, media delivery | Phase 1 |
| Cloud Compute | AWS ECS Fargate | Containerised serverless compute with auto-scaling | Phase 1 |
| File Storage | AWS S3 | PDF scorecards, knowledge base documents, media | Phase 1 |
| Monitoring | AWS CloudWatch + Sentry | Real-time metrics, error tracking, alerting | Phase 1 |
| Secrets | AWS Secrets Manager | API keys, credentials — zero hardcoding | Phase 1 |
| CI/CD | GitHub Actions + Docker | Automated testing, build, and deployment pipeline | Phase 1 |
| Auth | JWT + RBAC | API authentication, role-based portal access | Phase 1 |

## Architecture Overview

# 9.  Security & Compliance

Security is a foundational architecture requirement. The platform is designed to meet enterprise-grade security standards from Day 1 of deployment.

## Key Security Controls

- JWT authentication with refresh token rotation across all API endpoints

- Role-Based Access Control (RBAC) with least-privilege principle enforced across all portal and API layers

- End-to-end data encryption — at rest (AES-256 via AWS RDS + S3 SSE) and in transit (TLS 1.3)

- Secure webhook validation using HMAC-SHA256 signature verification on all inbound webhooks

- No payment or financial transaction processing is included within MVP Phase 1 scope. (PCI-DSS aligned)

- Audit logging for all administrative and transactional actions — CloudWatch structured logs

- AWS WAF and VPC isolation for network-layer protection

## Privacy, Security & Compliance Considerations

- The platform will follow industry-standard security and privacy practices for MVP Phase 1, including secure AWS hosting, role-based access control (RBAC), encryption of sensitive data, and user consent handling. GDPR-style data privacy principles and data minimisation practices will be considered where applicable.

- Formal compliance audits and certifications are outside the scope of MVP Phase 1.

Privacy Features

- Explicit user consent captured before any data collection, with timestamp and version tracking

- Right-to-be-forgotten support through data deletion or anonymisation requests

- All platform data and customer information remain the exclusive property of BA4E; CXION holds no ownership rights over customer data

- Data residency region (AWS eu-west-1 — Ireland or af-south-1 — Cape Town) to be finalized in consultation with BA4E

# 10.  Deliverables Summary

| # | Deliverable | Description | Format |
| --- | --- | --- | --- |
| 1 | WhatsApp Diagnostic Platform | Conversational diagnostic engine: onboarding + Categories A & B + scoring | Live (AWS) |
| 2 | Website Embedded Chatbot | JavaScript embed widget sharing the diagnostic backend; lead capture | Live (JS widget) |
| 3 | Diagnostic Scoring Engine | Real-time scoring using BA4E's pillar matrices and maturity classification | Live (FastAPI) |
| 4 | Dynamic PDF Scorecard Engine | Auto-generated branded scorecards delivered via WhatsApp within 60 seconds | Live (PDF / S3) |
| 5 | Future AI Advisory Architecture Preparation | Architecture planning and portal extensibility for future consultant advisory enhancement workflows . | Live (FastAPI) |
| 6 | Role-Based Consultant Portal | Next.js portal: dashboard, customers, reports, AI log, administration | Live (Next.js) |
| 7 | Account & API Configuration | WhatsApp Business API setup support, Secrets Manager, environment configuration | Supported setup |
| 8 | Cloud Deployment | AWS ECS Fargate, RDS, S3, CloudWatch with CI/CD pipeline | Live (AWS) |
| 9 | Technical Documentation | Architecture diagram, API docs, deployment guide, admin runbook | PDF / Markdown |

# 11.  Team Structure

| Role | Organisation | Responsibilities | Allocation |
| --- | --- | --- | --- |
| Solution Architect | CXION | Platform architecture, AI integration design, security model, phase gate sign-off | 100% |
| AI / ML Engineer | CXION | LangChain pipeline, ChromaDB setup, OpenAI integration, RAG quality testing | 100% |
| Backend Developer | CXION | FastAPI, PostgreSQL, scoring engine, PDF engine, webhook integrations | 100% |
| Frontend Developer | CXION | Next.js consultant portal, website chatbot widget, UI/UX implementation | 100% |
| DevOps Engineer | CXION | AWS ECS/RDS/S3, Terraform, CI/CD pipeline, CloudWatch, Secrets Manager | 100% |
| QA Engineer | CXION | Test strategy, unit/integration/E2E testing, UAT support and sign-off | Sprint 4 |
| Project Manager | CXION | Schedule, risk management, client liaison, milestone tracking, Change Control | 100% |
| BA4E Lead (Client) | BA4E | Knowledge base provision, content validation, UAT, approval authority | Key milestones |

## Client Obligations

To ensure timely delivery and successful implementation of the MVP Phase 1 solution, BA4E agrees to the following responsibilities and dependencies:

- Deliver all BA4E knowledge base documents (frameworks, SOPs, benchmarks, approved case studies, and reference materials) before the end of Week 1.

- Initiate the WhatsApp Business API application process with Meta on Day 1 of the engagement, acknowledging that approval timelines are managed by Meta and may typically require 2–4 weeks.

- Provide all diagnostic content, questionnaire sets, scoring matrices, and business rules in a structured and reviewable format before the end of Week 2.

- Provide CXION Technologies with the required AWS account access and appropriate permissions necessary for infrastructure setup, deployment, monitoring, and environment configuration activities.

- Assign a single authorized point of contact with decision-making authority for project approvals, requirement clarifications, and coordination activities.

- Provide consolidated written feedback within three (3) business days of each deliverable submission to avoid project delays.

- Participate actively in User Acceptance Testing (UAT) activities and provide formal written sign-off prior to production deployment.

# 12.  Project Timeline & Milestones

Total estimated duration: 8 Weeks from project kick-off, subject to timely delivery of BA4E content assets and completion of third-party API onboarding.

## Sprint Plan

| Sprint | Weeks | Activities | Milestone / Gate |
| --- | --- | --- | --- |
| Sprint 1 | 1–2 | Project kick-off • Architecture design and sign-off • AWS + GitHub environment setup • Database schema design • WhatsApp test credentials • Knowledge base ingestion begins | Architecture approved • Dev environment live |
| Sprint 2 | 3–4 | FastAPI core APIs • WhatsApp diagnostic flows (Categories A & B) • Scoring engine • PDF scorecard engine • Website chatbot widget | Diagnostic flows, scoring engine, and PDF delivery verified |
| Sprint 3 | 5–6 | AI Advisory Agent (LangChain + ChromaDB + OpenAI) • RAG pipeline testing and tuning • Consultant portal (Next.js) • Role-based access control • Dashboard and customer management | AI agent live • Portal accessible with all roles |
| Sprint 4 | 7–8 | Integration testing (all components) • Security review and penetration test • Performance testing (load, API latency) • UAT with BA4E stakeholders • Production deployment • Documentation and source code handover | UAT sign-off • Platform live • Handover complete |

## Milestone Schedule

| # | Milestone | Target | Gate Criteria |  |
| --- | --- | --- | --- | --- |
| M1 | Architecture Sign-Off | End of Week 1 | BA4E reviews and approves platform architecture |
| M2 | Diagnostics & PDF Live | End of Week 4 | Both diagnostics scoring correctly + PDF delivered (QA-verified) |
| M3 | AI Agent & Portal Live | End of Week 6 | AI agent responding contextually + portal accessible with all 3 roles |
| M4 | UAT Sign-Off | End of Week 8 | BA4E written sign-off on UAT completion report |
| M5 | Production Go-Live | End of Week 8 | Full platform live in production + handover complete |

Key dependency: WhatsApp Business API approval (Meta) must be initiated on Day 1 — independent review takes 2–4 weeks. Development proceeds on test credentials in parallel. Production go-live is gated on API approval.

# 13.  Testing & Acceptance

## Testing Approach

- Unit Testing — FastAPI endpoints, scoring logic, PDF generation, RAG retrieval, webhook handlers

- Integration Testing — WhatsApp API, ChromaDB, S3, AWS services

- End-to-End Testing — complete consultant workflow including diagnostics, scorecards, and internal AI advisory assistance, PDF delivery

- Performance Testing — API response time (target: p95 < 2 seconds at 1,000 concurrent users)

- Security Testing — RBAC validation, webhook HMAC, injection attacks, session management, data encryption

## User Acceptance Testing (UAT)

- UAT conducted with a defined BA4E pilot group in Sprint 4 (Weeks 7–8)

- BA4E receives a formal UAT test plan and sign-off checklist before UAT begins

- Defects categorised as Critical, Major, or Minor

- All Critical and Major defects must be resolved prior to go-live acceptance

- BA4E provides written sign-off on the UAT Completion Report before production deployment

## Acceptance Criteria

Final acceptance and production deployment is authorised when all of the following conditions are met:

- All in-scope features are functionally correct as per approved MVP Phase 1 specifications

- Security validation confirms all controls are active and effective

- BA4E provides written sign-off on the UAT Completion Report

# 14.  Deployment & Go-Live

Deployment follows a structured process to ensure stability, security, and operational readiness:

- Production environment provisioned on AWS ECS Fargate with appropriate compute, storage, and network configuration

- PostgreSQL RDS database provisioned with encryption at rest and automated backups enabled

- WhatsApp Business API configured and verified with all approved message templates

- AI Advisory Agent deployed with ChromaDB loaded; RAG responses validated against BA4E knowledge base

- PDF scorecard engine tested end-to-end — delivery within 60 seconds confirmed

- Monitoring, alerting, and logging enabled via AWS CloudWatch and Sentry

- Final data backup and rollback plan documented and tested

- Go-live coordinated with BA4E stakeholders; user acceptance sign-off confirmed

- Hypercare period: first 72 hours post go-live with real-time team availability; P1 response within 2 hours

# 15.  Assumptions

This SOW is prepared on the basis of the following assumptions. Material deviations may result in scope or timeline adjustments via formal Change Order:

- BA4E delivers all knowledge base documents, SOPs, frameworks, and benchmarks before end of Week 1

- BA4E initiates WhatsApp Business API application with Meta on Day 1 — approval timeline is outside CXION control

- BA4E provides all diagnostic content (question sets, scoring matrices) in structured format before Week 2

- OpenAI API access (GPT-4o) is provisioned and available before Sprint 3 commences

- The project proceeds in English only for the MVP; additional languages are Phase 2 scope

- Up to two rounds of consolidated written feedback per deliverable are included in scope; additional rounds are subject to Change Order

- AWS account (BA4E-owned or CXION-managed) is available with appropriate IAM permissions before Week 1

- BA4E participates actively in UAT and provides written sign-off before go-live

# 16.  Risks & Dependencies

## Risk Register

| # | Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | WhatsApp Business API approval delayed by Meta | High | High | Initiate Day 1. Build on test credentials in parallel. Production gated on approval. Client accepts this external dependency. |
| R2 | BA4E knowledge base documents not delivered on time | High | High | Hard deadline: end of Week 1. Delay triggers AI phase extension and formal Change Order. |
| R3 | AI-generated recommendations require consultant validation before customer delivery. | Medium | High | Comprehensive functional, integration, and workflow validation will be conducted during Sprint 3 and Sprint 4 to ensure platform stability, scoring accuracy, and production readiness prior to go-live. |
| R4 | Scope creep — requests for Phase 2 features mid-delivery | High | Medium | All out-of-scope work requires a signed Change Order. Section 17 governs the Change Control process. |
| R5 | PDF scorecard generation exceeds 60-second delivery SLA | Low | Medium | Load testing in Sprint 4. Async generation with WhatsApp callback. Template optimization if required. |

## Key Dependencies

| Dependency | Description | Required By |
| --- | --- | --- |
| WhatsApp Business API | Meta account approval and production phone number — BSP selection support provided by CXION | Day 1 |
| BA4E Knowledge Base | SOPs, frameworks, benchmarks, case studies in structured format | End of Week 1 |
| Diagnostic Content | Question sets, scoring matrices, maturity benchmarks validated by BA4E | Before Week 2 |
| BA4E Brand Assets | Logo, colour palette, PDF template design elements | Before Week 3 |
| AWS Account | BA4E or CXION-managed account with IAM permissions | Day 1 |
| OpenAI API Key | GPT-4o access — BA4E-owned or project-provisioned | Before Week 5 |

# 17.  Change Request Process

Any request for work outside the MVP Phase 1 scope defined in Section 6 must follow the formal Change Request process. No out-of-scope work commences without a fully executed Change Order signed by both parties.

| Step | Description |
| --- | --- |
| 1. Change Request Submission | BA4E submits written change request describing the requirement, business rationale, and priority |
| 2. Impact Assessment | CXION assess scope impact, technical complexity, and additional effort in person-days |
| 3. Timeline Review | Determine whether the change can be incorporated in the current sprint or requires extension |
| 4. Cost Review | Calculate additional cost based on effort estimate; present commercial impact to BA4E |
| 5. Change Order Issuance | Formal Change Order document issued detailing scope, effort, cost, timeline, and approval date |
| 6. Mutual Approval | Both parties must sign the Change Order before any development work commences |
| 7. Execution | Change incorporated into project plan; progress tracked against agreed milestones |

# 18.  Support & Maintenance

The following support packages are available following successful go-live:

| Package | Included Services | SLA / Response Time |
| --- | --- | --- |
| Standard (Included) | Bug fixes for defects found post go-live • Minor configuration adjustments • Security patches • Deployment support | 30-day warranty period • P1: 4 hours • P2: 8 hours • P3: Next business day |
| Extended Support | Priority bug fixes • Minor enhancements • Monthly health check • AI model tuning | P1: 2 hours • P2: 4 hours • P3: 8 hours • Monthly retainer — optional add-on |
| Managed Services | Full platform management • Feature development • Proactive monitoring • Phase 2 roadmap planning | Dedicated team • P1: 1 hour • Monthly retainer — scoped separately |

# 19.  Commercials

Commercial terms are fixed-price and milestone-based. All amounts are exclusive of applicable taxes. A fully executed SOW must be in place before work commences.

| Commercial Term | Details |
| --- | --- |
| Pricing Model | Fixed Price — Milestone-Based (MVP Phase 1) |
| Total Project Investment | USD |
| Currency | USD (United States Dollars) |
| Invoice Terms |  |
| Late Payment | 1.5% per calendar month on outstanding balances beyond agreed terms |
| IP Ownership | All custom code, models, and deliverables assigned to BA4E upon receipt of full final payment |
| Change Requests | All out-of-scope work requires a signed Change Order — see Section 17 |
| Phase 2 / Phase 3 | Separate SOW and commercial terms; subject to Phase 1 UAT sign-off and mutual agreement |

## Payment Schedule

| # | Milestone | Payment Trigger | Amount |
| --- | --- | --- | --- |
| 1 | SOW Signature & Project Initiation | Upon execution of fully signed SOW and project kickoff | 4200 USD |
| 2 | Design & Architecture Completion | UI/UX designs, solution architecture, questionnaire structure, and technical setup | 2100 USD |
| 3 | Core Platform Development Complete | Completion of WhatsApp workflows, website chatbot, diagnostic engine, scoring engine, consultant portal, and PDF scorecard generation | 6300 USD |
| 4 | UAT Completion | Completion of User Acceptance Testing (UAT) and BA4E review/approval of MVP deliverables | 4200 USD |
| 5 | Production Go-Live & Project Closure | Successful production deployment, knowledge transfer, technical documentation handover, and project closure | 4200 USD |
| ∑ | TOTAL | Fixed Price — MVP Phase 1 (USD) | 21000 USD |

# 20.  Agreement & Sign-Off

By signing below, both parties confirm that they have read, understood, and agreed to the terms set out in this Statement of Work. This document, together with any associated Master Services Agreement, constitutes the complete understanding between the parties for the BA4E MVP Phase 1 engagement.

|  |  | On Behalf of CXION Technologies Name: ____________________________ Title: ____________________________ Signature: ____________________________ Date: ____________________________ | On Behalf of BA4E (Client) Name: ____________________________ Title: ____________________________ Signature: ____________________________ Date: ____________________________ |
| --- | --- | --- | --- |

Please return a fully countersigned copy to initiate project kick-off. Kick-off can be scheduled within 3–5 business days of receipt of signed SOW.